## Simple Gantt chart
Task | Start date | End date
Business Problem | 2023-05-24 | 2023-05-26
Data Identification | 2023-05-28 | 2023-06-08
Literature Review | 2023-06-13 | 2023-06-28
Research Methodolgy | 2023-06-30 | 2023-07-06
Tools and Techlogies | 2023-07-09 | 2023-07-14
Data Analysis | 2023-07-16 | 2023-07-23
Segementation | 2023-07-25 | 2023-07-31
Business Recommendations | 2023-08-03 | 2023-08-05
Task | Start on day | Duration
Business Problem | 0 | 2
Data Identification | 5 | 11
Literature survey | 7 | 15
Research Methodolgy | 10 | 6
Tools and Techlogies | 10 | 5
Data Analysis | 23 | 7
Segementation | 27 | 6
Business Recommendations | 31 | 2

## Gantt chart with dependencies
Task | Dependency | Duration (Days) | Team | Owner | Task Start Date | Task End Date | Dep Start Date | Dep End Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Task 1 |  | 5 |  |  | 2021-08-05 | 2021-08-10 | N/A | N/A | bar: 5 to 10
Task 2 | Task 1 | 2 |  |  | 2021-08-10 | 2021-08-12 | 2021-08-05 | 2021-08-10 | bar: 10 to 12
Task 3 | Task 2 | 3 |  |  | 2021-08-12 | 2021-08-15 | 2021-08-10 | 2021-08-12 | bar: 12 to 15
Task 4 | Task 3 | 4 |  |  | 2021-08-15 | 2021-08-19 | 2021-08-12 | 2021-08-15 | bar: 15 to 19
Task 5 | Task 4 | 4 |  |  | 2021-08-19 | 2021-08-23 | 2021-08-15 | 2021-08-19 | bar: 19 to 23
Task 6 | Task 5 | 1 |  |  | 2021-08-23 | 2021-08-24 | 2021-08-19 | 2021-08-23 | bar: 23 to 24
Task 7 | Task 6 | 1 |  |  | 2021-08-24 | 2021-08-25 | 2021-08-23 | 2021-08-24 | bar: 24 to 25
Task 8 | Task 7 | 2 |  |  | 2021-08-25 | 2021-08-27 | 2021-08-24 | 2021-08-25 | bar: 25 to 27
Task 9 | Task 8 | 1 |  |  | 2021-08-27 | 2021-08-28 | 2021-08-25 | 2021-08-27 | bar: 27 to 28
Task 10 | Task 9 | 2 |  |  | 2021-08-28 | 2021-08-30 | 2021-08-27 | 2021-08-28 | bar: 28 to 30
Task 11 | Task 10 | 1 |  |  | 2021-08-30 | 2021-08-31 | 2021-08-28 | 2021-08-30 | bar: 30
Note on F2: Edit this date manually to have all other task start and end dates recalculate in a "cascading" fashion.